## Report
[Project Title] | [13 empty] | [Company Name / Logo]
Earned Value Analysis Report
| Prepared By: | [Manager's Name] |  |  |  |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
| Date: | [Report Date] |  |  |  | PV | 1350 | 6670 | 17310 | 30220 | 41500 | 49840 | 56940 | 61420 | 66280 | 73520 | 75140 | 75140
|  | [42] |  |  |  | EV | 1150 | 6704 | 13173 | 20077 | 27616 | 36724 | 44972 | 44972 | 44972 | 44972 | 44972 | 44972
| For Period: | Week xxx |  |  |  | AC | 700 | 4390 | 13310 | 20810 | 33930 | 42770 | 51410 | 51410 | 51410 | 51410 | 51410 | 51410
[6 empty] | EAC | 102440.5303 | 98493.459 | 98518.2098 | 96524.8104 | 99278.2493 | 95594.2224 | 92892.7452 | 92892.7452 | 92892.7452 | 92892.7452 | 92892.7452 | 92892.7452
Summary:
[Use this space to write a brief summary or to record specific observations or notes]
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | Total | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 |  | ← You can change the labels for the periods (e.g. Week 1/2/3, Jan/Feb/Mar, etc.)
1.1 | Task 1 | 7500 | 1350 | 1200 | 3400 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ← Enter or edit values in the light-gray cells.
| Goods & Services | 4000 | 1000 | 500 | 2000 | 500
| Manhours (WS) | 100 | 10 | 20 | 40 | 30
| Hourly rate (BC) |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
1.2 | Task 2 | 27600 | 0 | 3000 | 5000 | 8000 | 6800 | 3300 | 1500 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 5200 |  | 200 | 800 | 2400 | Wk 1: 1200; Wk 2: 500; Wk 3: 100
| Manhours (WS) | 640 |  | 80 | 120 | 160 | Wk 1: 160; Wk 2: 80; Wk 3: 40
| Hourly rate (BC) |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
1.3 | Task 3 | 33040 | 0 | 1120 | 2240 | 3360 | 4480 | 5040 | 5600 | 4480 | 3360 | 2240 | 1120 | 0
| Goods & Services | 0
| Manhours (WS) | 1180 |  | 40 | 80 | 120 | Wk 1: 160; Wk 2: 180; Wk 3: 200; Wk 4: 160; Wk 5: 120; Wk 6: 80; Wk 7: 40
| Hourly rate (BC) |  | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
1.4 | Task 4 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 5000 | 500 | 0
| Goods & Services | 7000 |  |  |  |  | Wk 5: 1500; Wk 6: 5000; Wk 7: 500
| Manhours (WS) | 0
| Hourly rate (BC) |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
1.5 | Task 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
1.6 | Task 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
1.7 | Task 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
1.8 | Task 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
1.9 | Task 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
2 | Task 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
2.1 | Task 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
2.2 | Task 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
Insert new rows above this one
| Total Budgeted Cost | 75140 | 1350 | 5320 | 10640 | 12910 | 11280 | 8340 | 7100 | 4480 | 4860 | 7240 | 1620 | 0
| Cumulative Planned Value (PV) |  | 1350 | 6670 | 17310 | 30220 | 41500 | 49840 | 56940 | 61420 | 66280 | 73520 | 75140 | 75140 | ok
Cumulative Earned Value (EV)
WBS | Task Name | Total | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Task 1 | 7500 | 1150 | 2250 | 1525 | 1100 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 100% | 20% | 30% | 25% | 10% | Wk 1: 15%
| Manhours (WS) | 100% | 10% | 30% | 15% | 20% | Wk 1: 25%
| Hourly rate (BC) |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
1.2 | Task 2 | 11040 | 0 | 0 | 1640 | 2500 | 2760 | 2500 | 1640 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 40% |  |  | 10% | 5% | Wk 1: 10%; Wk 2: 5%; Wk 3: 10%
| Manhours (WS) | 40% |  |  | 5% | 10% | Wk 1: 10%; Wk 2: 10%; Wk 3: 5%
| Hourly rate (BC) |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
1.3 | Task 3 | 26432 | 0 | 3304 | 3304 | 3304 | 3304 | 6608 | 6608 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 80% |  |  |  | 20% | Wk 1: 20%; Wk 2: 20%; Wk 3: 20%
| Manhours (WS) | 80% |  | 10% | 10% | 10% | Wk 1: 10%; Wk 2: 20%; Wk 3: 20%
| Hourly rate (BC) |  | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
1.4 | Task 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0%
| Manhours (WS) | 0%
| Hourly rate (BC) |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
1.5 | Task 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0%
| Manhours (WS) | 0%
| Hourly rate (BC) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | Task 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0%
| Manhours (WS) | 0%
| Hourly rate (BC) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 | Task 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0%
| Manhours (WS) | 0%
| Hourly rate (BC) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 | Task 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0%
| Manhours (WS) | 0%
| Hourly rate (BC) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | Task 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0%
| Manhours (WS) | 0%
| Hourly rate (BC) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Task 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0%
| Manhours (WS) | 0%
| Hourly rate (BC) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Task 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0%
| Manhours (WS) | 0%
| Hourly rate (BC) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Task 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0%
| Manhours (WS) | 0%
| Hourly rate (BC) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Insert new rows above this one
|  | 44972 | 1150 | 5554 | 6469 | 6904 | 7539 | 9108 | 8248 | 0 | 0 | 0 | 0 | 0
| Cumulative EV |  | 1150 | 6704 | 13173 | 20077 | 27616 | 36724 | 44972 | 44972 | 44972 | 44972 | 44972 | 44972 | ok
Actual Cost (AC) of Work Performed
WBS | Task Name | Total | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Task 1 | 6890 | 700 | 1290 | 2680 | 1060 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 3050 | 700 | 650 | 1400 | 100 | Wk 1: 200
| Manhours (WS) | 120 |  | 20 | 40 | 30 | Wk 1: 30
| Hourly rate (BC) |  | 32 | 32 | 32 | 32 | Wk 1: 32
1.2 | Task 2 | 21120 | 0 | 0 | 3840 | 4040 | 6560 | 3440 | 3240 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 4400 |  |  | 800 | 1000 | Wk 1: 2000; Wk 2: 400; Wk 3: 200
| Manhours (WS) | 440 |  |  | 80 | 80 | Wk 1: 120; Wk 2: 80; Wk 3: 80
| Hourly rate (BC) |  |  |  | 38 | 38 | Wk 1: 38; Wk 2: 38; Wk 3: 38
1.3 | Task 3 | 23400 | 0 | 2400 | 2400 | 2400 | 5400 | 5400 | 5400 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 780 |  | 80 | 80 | 80 | Wk 1: 180; Wk 2: 180; Wk 3: 180
| Hourly rate (BC) |  |  | 30 | 30 | 30 | Wk 1: 30; Wk 2: 30; Wk 3: 30
1.4 | Task 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
1.5 | Task 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
1.6 | Task 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
1.7 | Task 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
1.8 | Task 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
1.9 | Task 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
2 | Task 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
2.1 | Task 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
2.2 | Task 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goods & Services | 0
| Manhours (WS) | 0
Hourly rate (BC)
Insert new rows above this one
| Total Actual Cost | 51410 | 700 | 3690 | 8920 | 7500 | 13120 | 8840 | 8640 | 0 | 0 | 0 | 0 | 0
| Cumulative Actual Cost (AC) |  | 700 | 4390 | 13310 | 20810 | 33930 | 42770 | 51410 | 51410 | 51410 | 51410 | 51410 | 51410 | ok
Actual Cost and Earned Value
| Cumulative Actual Cost (AC) |  | 700 | 4390 | 13310 | 20810 | 33930 | 42770 | 51410 | 51410 | 51410 | 51410 | 51410 | 51410
| Cumulative Earned Value (EV) |  | 1150 | 6704 | 13173 | 20077 | 27616 | 36724 | 44972 | 44972 | 44972 | 44972 | 44972 | 44972
Project Performance Metrics |  | avg
| Cost Variance (CV = EV - AC) |  | 450 | 2314 | -137 | -733 | -6314 | -6046 | -6438 | -6438 | -6438 | -6438 | -6438 | -6438
| Schedule Variance (SV = EV - PV) |  | -200 | 34 | -4137 | -10143 | -13884 | -13116 | -11968 | -16448 | -21308 | -28548 | -30168 | -30168
| Cost Performance Index (CPI = EV/AC) | 1.0038 | 1.6429 | 1.5271 | 0.98971 | 0.96478 | 0.81391 | 0.85864 | 0.87477 | 0.87477 | 0.87477 | 0.87477 | 0.87477 | 0.87477
| Schedule Performance Index (SPI = EV/PV) | 0.72449 | 0.85185 | 1.0051 | 0.76101 | 0.66436 | 0.66545 | 0.73684 | 0.78981 | 0.7322 | 0.67852 | 0.6117 | 0.59851 | 0.59851
| Predicted Cost Index (PCI = (EAC-AC)/(PV-EV)) |  | 1.3751 | 1.3751 | 1.3751 | 1.3751 | 1.3751 | 1.3751 | 1.3751 | 1.3751 | 1.3751 | 1.3751 | 1.3751 | 1.3751
| Estimated Cost at Completion (EAC) | 1) | 74690 | 72826 | 75277 | 75873 | 81454 | 81186 | 81578 | 81578 | 81578 | 81578 | 81578 | 81578
| Estimated Cost at Completion (EAC) | 2) | 45737.3913 | 49204.1468 | 75921.4606 | 77883.3192 | 92319.677 | 87510.5599 | 85896.7224 | 85896.7224 | 85896.7224 | 85896.7224 | 85896.7224 | 85896.7224
| Estimated Cost at Completion (EAC) | 3) | 53569.9811 | 48976.8674 | 95584.6817 | 106717.0432 | 121675.2055 | 103489.6793 | 95074.3684 | 98509.8508 | 102236.7358 | 107788.7208 | 109031.0158 | 109031.0158
| Estimated Cost at Completion (EAC) | 3*) | 102440.5303 | 98493.459 | 98518.2098 | 96524.8104 | 99278.2493 | 95594.2224 | 92892.7452 | 92892.7452 | 92892.7452 | 92892.7452 | 92892.7452 | 92892.7452
1) EAC = PV+AC-EV
2) EAC = PV+(AC-EV)/CPI
3) EAC = PV+(AC-EV)/(CPI*SPI)
3*) EAC = PV+(AC-EV)/(avgCPI*avgSPI)
Note on A28: Work Breakdown Structure (WBS)